## Sheet1
Hoey Report Action Plan | Key
Bold = Completed
Recommendation | Comment | March | April | May | June | July | August | Sep | Oct | Nov | Dec | Jan | Feb | March | April | May
The Parish Council should formalise the separation of CIC meetings (called SFF Committee) from Full Council meetings. | The SFF Committee meetings have been suspended until a new clerk has been employed due to the ongoing high costs of a locum clerk.
To undertake a full audit of the CIC Management Agreement and reporting on the CIC lease. There is a need for the scrutiny of CIC management accounts and use of funding to be assessed and a process for proper definition and accounting to be put into place by the Parish Council.
There need to be agreed objectives between the CIC and the Parish Council and there should be regular reporting back from the CIC to the Parish Council against those agreed objectives.
The Parish Council should consider its staffing requirements to ensure that it is properly resourced to support its scrutiny of the CIC. This may include appointing a CIC Liaison Officer or more generally a project officer so that there is better liaison and scrutiny of the CIC and the Parish Council’s interests are better protected. | This will need to be taken into account during the budget setting schedule.
To review the Terms of Reference of the SFF Committee and consider with the CIC whether the Parish Council Chair and/or Deputy Chair should be ex officio directors of the CIC. This should include an agreement as to what matters are delegated to the Committee and which issues relating to the CIC must be signed off by Full Council. | This was completed and agreed in May. |  |  | C
The Parish Council should work with the CIC and wider community to develop a strategic plan for the village including the use of SFF (see section below on wider vision for the Council). This should include in particular a 10-year plan for the CIC with measurable targets and objectives to allow for proper budget forecasting and management.
That the Council put in place a detailed training programme on the role of the parish councillor, understanding the role of the Clerk, understanding delegated authority, chairing and meeting skills, the Code of Conduct (in particular to improve understanding of requirements around registration and declarations of interest), financial regulations and other matters. | Councillor and Chairman training undertaken by whole council on 31 May |  |  | C
That councillors recognise that they cannot speak on behalf of the Council unless authorised by the Full Council to do so. Any correspondence from individual councillors needs to make this clear. | This was covered under councillor and chairman training |  |  | C
The Council should develop an agreed understanding of the role and expectations for individual councillors when they are acting as Full Council, as committee members, as individuals and as representatives of the Council externally. | The council has signed up to the debate not hate campaign and the cilvility and respect pledge. Although this was undertaken in April, the new council has also familiarised itself with the content. |  | C
That councillors understand their fiduciary duties and vicarious liability and be reminded that they are all individually and severally liable for the finances and employment practices of the Council. Individual councillors should therefore be reminded that they should not act alone and unilaterally once Council collectively has made a decision or agreed a course of action. Nor should councillors act alone on issues such as tree felling without proper insurance and risk assessment. | This was covered under councillor and chairman training. The council are also now made aware of the financial position and will be looking at this every month, every expenditure is asked which budget the monies are coming from, this is minuted and unbudgeted expenditure will also be minuted. |  |  | C
The Council needs to review its staffing needs. In particular it needs to recruit a permanent Clerk who is CiLCA qualified. | The HR meeting is taking place in June and recommended to FC in July - the clerk role will then be advertised.
The Council and the Clerk should agree a work schedule to ensure that staff’s limited availability is focussed and that there are realistic expectations on their time. | The locum clerk has compliled a list of outstanding actions and current actions so that realistic expectations can be set.
The Council needs to agree a councillor-officer protocol which would include a shared agreement as to the circumstances when councillors should have access to officer time and how the clerk should respond to queries from individual councillors.
The Council should review its policy as to how correspondence is dealt with and responded to without absorbing the limited administrative resources available to the Council. This would include an agreed policy for dealing with persistent or vexatious correspondence.
The Council should agree how governance issues should be raised in meetings to allow reasonable discussion but also to allow other business to be transacted. | These should be raised in meetings with the Clerk advising the standing orders. There should be no arguments with a CILCA trained clerk. This was explained in training. |  |  | C
Once the Council has set a long-term strategy it should review whether its current staffing structure is in line with that strategy and able to help the Council deliver it and that the Clerk’s key performance objectives and time are geared to deliver that strategy. | This could take a long time to deliver as there is not the manpower to set strategy for the next 12 months. This will be in the next municipal year.
The Council need to understand and recognise the role of the Clerk and RFO to ensure health and safety regulations are being adhered to and any actions requiring payments are shown to be transparent and according to financial regulations. | Payments are now being signed as per financial regs and bank mandates have been sent off so two cllrs can sign off. H&S docs are being requested via the locum clerk. |  |  | C
The Council should ensure that the Clerk and the Council make best use of external support and advice from its memberships of professional bodies. | Ongoing
The Council should ensure that there is an appropriate performance appraisal framework in place for the Clerk which supports development of the Clerk and ensures performance is rewarded accordingly. | This will be put in place on the recruitment of a new clerk via a staffing sub committee of the Finance & HR committee.
The Parish Council should sign up to the Civility & Respect Pledge and collectively agree what language is and is not appropriate in meetings and correspondence among councillors and with the Clerk, how such language should be challenged in meetings and how meetings can be run more efficiently without getting bogged down in minutiae nor stifling legitimate debate. Behaviour needs to be re-set. | This has been signed up to and meetings are running better |  | C
The Council needs to adopt an email policy, for example that no member shall send more than two emails a day to the Clerk and no email should be more than a page of A4 in length. If the policy is breached the Clerk will simply reply to say that the email will not be responded to as it falls outside the policy. There may be exceptions for significant urgent matters but the Council as a whole shall agree a definition of what those exceptions should be. All emails should go through the Clerk.
All councillors should give an undertaking to treat fellow councillors and officers with respect and not to make personal attacks on individuals or their integrity. Until such respect is shown the Council cannot move forward. If personal attacks are made in future the matter should be referred to Rother District Council who will deal with the matter against set criteria and will ensure that anything that falls below the Council’s agreed standards is appropriately dealt with and breaches of the Code are sanctioned and publicised. | Dignity at Work Policy has been agreed and signed by all councillors |  | C
All councillors should undertake that, where they have concerns about the way a decision has been made or a procedure followed they should discuss this with the Clerk and the Clerk should be allowed to give a ruling with reasons such as a reference to existing policy or legislation as to whether or not the concern is legitimate. This ruling should be communicated to all councillors. Where the concern is legitimate such a ruling should include the steps needed either to rectify the matter with an agreed timescale or the changes needed to prevent the matter re-occurring. Where the majority of councillors accept that the concern has been dealt with, the matter cannot be raised again for six months. | Ongoing
The Council needs to update its Standing Orders and Financial Regulations. |  |  |  | C
Payment of accounts needs to be resolved immediately and the Council needs to formalise the role of RFO and financial matters need to be put onto a firmer footing, in particular with proper budgeting measures implemented. | Bank mandates have been sent off so awaiting two signatories, role of locum RFO in place.
A full suite of policies need to be in place and published on the website. These should include: • Equal Opportunities Policy • Disciplinary and Grievance Policy • Health and Safety Policy • Sickness and Absence Policy • Code of Conduct, Complaints Policy - completed April 23 • Councillor-Officer Protocol - completed April 23 • FOI requests and publication scheme - completed May 23 • Data Protection (GDPR) Policy - completed May 23 • Bullying Policy - completed April 23 • Recording of Meetings Policy
The Council need to formalise a Trees and Open Space Maintenance Policy, and Severe Weather Policy with appropriate Risk Assessments in place.
The Council needs to adopt a Communications and Social Media Policy which would cover both appropriate use of social media by individuals and the Council’s own approach to communications and social media as an organisation. In particular it should consider producing its own newsletter to be delivered to every household in the parish, and to develop a Facebook page. | This will be for the new clerk.
All councillors need to be familiar with Standing Orders and should have a pack which contains all policies, Financial Regulations and Standing Orders that they bring to each and every meeting to aid understanding and avoid confusion.
The ‘three-minute’ rule in Standing Orders should be enforced and all councillors should support the Chair in ensuring the meeting is run efficiently and without conflict. The rule may be waived in exceptional circumstances where an agenda item is of particular significance but this must be agreed at the start of the agenda item and a revised time limit (say five minutes) agreed. | Completed - the Chairman monitors this. (June 23)
The Council should set an agenda with indicative timings so that the meeting can be progressed and the timetable waived only with agreement at the meeting. | This will be for the new clerk.
The Council needs to have clear rules for public participation which should limit contributions to allow council business to progress. | Councillors have been directed to standing orders in relation to public participation and the Chairman monitors this. (June 23)
Minutes should be agreed at the following meeting. Amendments can only be proposed by those who attended the meeting and should be factual only rather than opinion. | Minutes are now resolutions only and are signed at the next meeting. (June 23)
Minutes are a record of the decisions made at meetings and whilst some brief narrative is required they should not be verbatim but should serve to help anybody understand the process by which a decision is made. So they should be written to make clear the decision taken with some brief summary of matters considered for and against. | Minutes are now factual and are not verbatim. (June 23)
Meetings should be uploaded to the website with supporting papers and the web pages of the Council kept up to date with councillor details and a link to registers of interests. | This is being undertaken by Locum Clerk.
The Council should develop a process for strategic planning with a view to the new Council developing a strategic plan for its term of office, to be agreed by the Council collectively. This should be a fully costed and resourced long-term strategic plan for the parish and the community, including strategic aims for SFF. | This will be for the new clerk.
The Council should engage with the community and with the CIC in developing its long-term plan and should review its communication strategy in conjunction with the public to evaluate its effectiveness and ensure that the public understands the work of the Parish Council, is engaged in developing a vision for Northiam and is able to participate more fully in local decision-making. This engagement work needs to demonstrate the value of the Council to the community and encourage the community to become engaged in shaping the future. | This will be for the new clerk.
The Council Chair and Clerk should look to learn from and share best practice with outstanding local councils both in developing strategy and a communications policy. | This will be ongoing.
Where Northiam Parish Council needs to use external support to comply with these recommendations, they should consult with Rother District Council and the East Sussex Association before agreeing such support to ensure they have considered all the options and are obtaining expert advice at value for money. | This will be ongoing.
Northiam Parish Council should develop an initial implementation plan within six weeks of receipt of the report which should be shared with the Monitoring Officer of Rother District Council. They should also report on their progress in implementing this action plan to the monitoring officer in six months and again in 12 months after the date of the plan. | This table will be the implementation plan
If the new Council is still not operating effectively and relationships have not improved after this 12-month review Rother District Council should consider a full review of the viability of the Council continuing